## Numeric
Ref | General area | Location | Situation |  | Status | Date updated | Update | Date added | Photo
1 | Leith Walk Northbound | York Place | Junction | Jn now fully open and CCWEL cycleway re-opened. | Closed |  |  | 2023-05-04 | 1990
2 | Leith Walk Northbound | York Place | Crossing | Toucan from North cycleway completed. Cross via island: 1. Crossing is staggered with little room in the middle (on the platform) and lots of poles in the way, making it virtually unrideable. 2. Crossing lights are live to the main island but crossing goes nowhere except tramstop island and assume trams aren't stopping yet? 2. Crossing needs to be adapted to support northbound cyclists joining the carriageway. |  | 2023-06-22 | Crossing completed except for Northbound cycle signals. Design for cycle route to Gayfield awaited. (see 3) | 2023-05-04 | 1991 1992 1993
3 | Leith Walk Northbound | Picardy Place/ Antigua Street | Add facility | Cycleway along North side from Toucan to Gayfield Square. |  |  |  | 2023-05-04 |  | Awaiting survey to determine whether there is space
4 | Leith Walk | General | Crossing | Do all the junctions with cycle facilities support cyclists U-turns? (Manderston St looks very awkward.) | Query |  |  | 2023-05-04
5 | Leith Walk | General | Resurfacing | Will resurfacing of adjacent streets eg Montgomery and Brunswick be carried out? | Query |  |  | 2023-05-04
6 | Leith Walk Northbound | London Road | Under construction | When will cycleway from Omni to London Road be completed? | Query |  |  | 2023-05-04
7 | Leith Walk Northbound | Elm Row | Under construction | When will Elm Row cycleways be completed? | Query |  |  | 2023-05-04
8 | Leith Walk Northbound | Leith Walk | Under construction | When will Leith Walk cycleway be completed and officially OPEN | Query |  |  | 2023-05-04
9 | Leith Walk Northbound | London Road | ASL | ASL needed Northbound from Picardy Place. Ideally to link with on-road cycleway. Also to accommodate right-turning on-road cyclists? Include cycle early release. |  |  |  | 2023-05-04
10 | Leith Walk | Leith Walk | Pavement Parking | What is proposed to resolve the issues with pavement parking? | Query |  |  | 2023-05-04
11 | Leith Walk | Leith Walk | Driver behaviour | Is there still a problem with illegal manoeuvres eg Left turn into London Road and Strraight across from McDonald Rd into Brunswick? | Query |  |  | 2023-05-04
12 | Leith Walk | Leith Walk | Driver behaviour | What is proposed re Brunswick St? | Query |  |  | 2023-05-04
13 | Leith Walk Northbound | Leith Walk | Driver behaviour | What is proposed re Driver Behaviour eg re continuous footways; pavement parking; illegal manoeuvres? | Query 1 |  |  | 2023-05-04
14 | Leith Walk Northbound | Gayfield Square | Collapsed manhole | Temporary cover in place - needs fixing. | o/s 3 |  |  | 2023-05-04
15 | Leith Walk Northbound | Gayfield Square | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
16 | Leith Walk Northbound | Gayfield Square | White lining | Oustanding at bus stop | o/s 1 |  |  | 2023-05-04
17 | Leith Walk Northbound | Elm Row | Crossing | No signals for westbound cyclists | ??? |  |  | 2023-05-04
18 | Leith Walk Northbound | Annandale St | Crossing | Cyclist call button says "pedestrians" and "signal opposite". Isn't obviously for cycle crossing as in line w ped xing of Annandale. | Fault 3+ |  |  | 2023-05-04
19 | Leith Walk Northbound | Annandale St | White lining | White lining on North side oustanding | o/s 1 |  |  | 2023-05-04
20 | Leith Walk Northbound | Annandale St | Barriers | Why are the barriers here - no signage. Is it to show that cycleway is closed? | Query |  |  | 2023-05-04
21 | Leith Walk Northbound | Annandale St | Surface | Access slip to cycleway from Annandale appears unfinished and no red chips. | Closed | 2023-06-22 | Completed | 2023-05-04
22 | Leith Walk Northbound | Leith Walk | Other works | Is the the raised white lining from the temporary cycleway going to be removed? | Query |  |  | 2023-05-04
23 | Leith Walk | Leith Walk | Other works | Are all the broken slabs going to be replaced? | Query (Fault 5) |  |  | 2023-05-04
24 | Leith Walk Northbound | 5th Season Vintage | Cycleway geometry | Very tight turn in cycleway | Fault 4 |  |  | 2023-05-04
25 | Leith Walk Northbound | Leith Walk | Cycleway geometry | Have all the non-conformant tight turns been remedied? | Query (Fault 4) |  |  | 2023-05-04
26 | Leith Walk Northbound | Leith Walk | Buffer Zone | What is happening about the buffer zone incursions? | Query |  |  | 2023-05-04
27 | Leith Walk Northbound | Emma Hall | Other works | Broken slab | Fault 5 |  |  | 2023-05-04
28 | Leith Walk Northbound | Emma Hall | White lining | Oustanding | o/s 1 |  |  | 2023-05-04
29 | Leith Walk Northbound | Tribe Yoga area | Poor surface | Cycleway edge breaking up. (General problem?) | Fault 6 |  |  | 2023-05-04
30 | Leith Walk Northbound | McD Rd library | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
31 | Leith Walk Northbound | McD Rd library | Poor surface | Badly repaired. Former lampost position? | Closed ? | 2023-06-22 | Completed ? | 2023-05-04
32 | Leith Walk Northbound | McD Rd library | Surface | Wrong surface finish | Fault 7 |  |  | 2023-05-04
33 | Leith Walk Northbound | Leith Walk | Poor surface | When will all the temporary lampost hole repairs be completed? | Query ? | 2023-06-22 | Completed? | 2023-05-04
34 | Leith Walk Northbound | Red Cross (McD Rd) | Buffer Zone | Large deviation for tiny inspection cover couldn't it be covered? | Design |  |  | 2023-05-04
35 | Leith Walk Northbound | General | General | What will happen re items that TtN are not addressing? | Query |  |  | 2023-05-04
36 | Leith Walk Northbound | The Walnut | Cycleway geometry | Cycleway changes direction twice in short space - combine into single direction change | Design |  |  | 2023-05-04
37 | Leith Walk Northbound | Engine Yard | Poor surface | Repair needed but not marked | o/s 3 |  |  | 2023-05-04
38 | Leith Walk Northbound | Places Gym | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
39 | Leith Walk Northbound | Sainsbury | Obstruction | Sign-pole too close to cycleway at informal crossing | Fault 9 |  |  | 2023-05-04
40 | Leith Walk Northbound | Sainsbury | Poor surface | Large manhole cover missing | o/s 3 |  |  | 2023-05-04
41 | Leith Walk Northbound | Sainsbury | Other works | Broken slab | Fault 5 |  |  | 2023-05-04
42 | Leith Walk Northbound | No 372 | Poor surface | Repair needed - marked | o/s 3 |  |  | 2023-05-04
43 | Leith Walk Northbound | Scotmid | Poor surface | Cracked edging | Fault 6 |  |  | 2023-05-04
44 | Leith Walk Northbound | Pilrig St jn | Poor surface | Puddle on south side | Fault 2 |  |  | 2023-05-04
45 | Leith Walk Northbound | Pilrig St jn | Signals | Call signal refers to pedestrians and unclear what crossing it's for | Fault 3 |  |  | 2023-05-04 |  | Also at Annandale
46 | Leith Walk Northbound | Pilrig St jn | Poor surface | North side - collapsed manhole | o/s 3 |  |  | 2023-05-04
47 | Leith Walk Northbound | Pilrig area? | Poor surface | Puddles | Fault 2 |  |  | 2023-05-04
48 | Leith Walk Northbound | Chinese Mkt | Crossing | Cycle stop line and cycle signal - when are cyclists held at ped signalised crossings? Just on pedestrian phase? | Query |  |  | 2023-05-04
49 | Leith Walk Northbound | Chinese Mkt | Poor surface | Puddles before and after | Fault 2 |  |  | 2023-05-04
50 | Leith Walk Northbound | Balfour St jn | White lining | oustanding | o/s 1 |  |  | 2023-05-04
51 | Leith Walk Northbound | Rome Barber | White lining | Cycle logo needs redone | o/s 4 |  |  | 2023-05-04
52 | Leith Walk Northbound | Lorne Street | Crossing | Signalised ped crossing but no cycle stop signal. | Query |  |  | 2023-05-04 |  | As cycleway is set back from carriageway - ie "floating" crossing?
53 | Leith Walk Northbound | Springfield St / General | Continuous footway | Cycle symbol on South side should be nearer to jn so that cyclists from Springfield St see that flow is northbound. | Design |  |  | 2023-05-04 |  | Needs applying elsewhere and relates to cyclists' u-turns to reach eastern cycleway
54 | Leith Walk Northbound | Steads Place | Other works | Damaged slabs | Fault 5 |  |  | 2023-05-04
55 | Leith Walk Northbound | Steads Place | Poor surface | Lots of puddles to north | Fault 2 |  |  | 2023-05-04
56 | Leith Walk Northbound | Leith Depot | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
57 | Leith Walk Northbound | Leith Depot/ General | Cycleway geometry | Turn too tight | Fault 4 |  |  | 2023-05-04 | 2043
58 | Leith Walk Northbound | Leith Depot/ General | Obstruction | Tram warning signpole too close to cycleway | Fault 9 |  |  | 2023-05-04 | 2044
59 | Leith Walk Northbound | Mother Superior | Poor surface | Large puddle | Fault 2 |  |  | 2023-05-04 | 2045
60 | Leith Walk Northbound | Mother Superior | Crossing | No cycle stop line or signals | o/s 4? |  |  | 2023-05-04 | 2045
61 | Leith Walk Northbound | No 62 | Other works | Large puddle on footway | Fault 2 |  |  | 2023-05-04 | 2048
62 | Leith Walk Northbound | Casselbank | Obstruction? | Pole quite close to cycleway (over 500mm though) | Fault 9? |  |  | 2023-05-04 | 2050/ 2051
63 | Leith Walk Northbound | No 34 | Poor surface | Large puddle in cycleway followed by general puddling | Fault 2 |  |  | 2023-05-04 | 2052/ 2053
64 | Leith Walk Northbound | Foot of the Walk | Crossing | Unfinished. Some cycle signals covered up or turned off but pushbutton illuminated. | Design? |  |  | 2023-05-04 | 2054/ 2055
65 | Leith Walk Southbound | Foot of the Walk | Cycleway geometry | Very narrow lane on SE corner | o/s? |  |  | 2023-05-04 | 2056/ 2057 | Spokes told that this would be fixed?
66 | Leith Walk Southbound | Foot of the Walk | Surface | some sections with white chippings - eg at Argonaut Books | Fault 7 |  |  | 2023-05-04 | 2058
67 | Leith Walk Southbound | TSB | Poor surface | Poor repair | o/s 3 |  | Maybe complete if was from lamp post removal | 2023-05-04 | 2060
68 | Leith Walk Southbound | Papa John's | Poor surface | Puddles | Fault 2 |  |  | 2023-05-04 | 2061
69 | Leith Walk | General | Poor surface | What sections are being resurfaced and when? | Query / Some Fault 2? |  |  | 2023-05-04
70 | Leith Walk | General | Cycleway delineation | Is anything further planned to aid cycleway delineation for partially sighted. Are cyclists still having problems with it? | Query |  |  | 2023-05-04
71 | Leith Walk Southbound | Manderston St | Cycle crossing | Different design from the crossroads junctions. Why no red surfacing? What is the phasing? How do southbound cyclists turn right for a U-turn? | Query? | 2023-06-20 | Cycle signals only seem to change in phase after a tram passes. South ped signal off. | 2023-05-04 | 2064/2065
72 | Leith Walk | General | White lining | When will it all be finished? | Query |  |  | 2023-05-04
73 | Leith Walk Southbound | Tip Top Tresses | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
74 | Leith Walk Southbound | Salvation Army | Cycleway geometry | 2-stage deviation should be combined | Design |  |  | 2023-05-04
75 | Leith Walk Southbound | 129 | Poor surface | Puddling |  |  |  | 2023-05-04
76 | Leith Walk Southbound | Allander House | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
77 | Leith Walk Southbound | ex Tram Offices | Other works | Crossing needs to be done | o/s |  |  | 2023-05-04
78 | Leith Walk Southbound | ex Tram Offices | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
79 | Leith Walk Southbound | Smiths Place | White lining | No arrows on ramp | o/s 1 |  |  | 2023-05-04
80 | Leith Walk Southbound | Casino Gaming | Poor surface | Puddles | Fault 2 |  |  | 2023-05-04
81 | Leith Walk Southbound | William Hill | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
82 | Leith Walk Southbound | Lorne Street | Crossing | No cycle stop line or signals - as elsewhere? | Query design |  |  | 2023-05-04 |  | Is this because the cycleway is set back?
83 | Leith Walk Southbound | Lorne Street | Obstruction | Bin a bit close to cycleway | Fault 9 |  |  | 2023-05-04
84 | Leith Walk Southbound | Jameson Place | White lining | Ramp without arrows | o/s 1 |  |  | 2023-05-04
85 | Leith Walk Southbound | Jameson Place | Cycleway geometry | Sharp turn | Fault 4 |  |  | 2023-05-04
86 | Leith Walk Southbound | Jameson Place | Obstruction | Pole in cycleway | Fault 9 |  |  | 2023-05-04 | 2082
87 | Leith Walk Southbound | Home essentials | Poor surface | Puddles | Fault 2 |  |  | 2023-05-04
88 | Leith Walk Southbound | Iona Street | Poor surface | Bad repair | o/s 3 |  |  | 2023-05-04
89 | Leith Walk Southbound | Pilrig St jn | Cycleway Design | No stop signal for southbound cyclists eg for when pedestrians and cyclists crossing | Query design |  |  | 2023-05-04
90 | Leith Walk Southbound | Pilrig St jn | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
91 | Leith Walk Southbound |  | Poor surface | Bad repair - ex lampost? | o/s 3 |  |  | 2023-05-04
92 | Leith Walk Southbound | A-os Barbers | Poor surface | Bad repair - ex lampost? | o/s 3 |  |  | 2023-05-04
93 | Leith Walk Southbound | Albert Street | Crossing Design | Crossing from Northbound very tight if doing a U-turn | Query design |  |  | 2023-05-04
94 | Leith Walk Southbound | Green Leith | Poor surface | Bad repair - ex lampost? | o/s 3 |  |  | 2023-05-04
95 | Leith Walk Southbound | Gateway Apartments | Poor surface | Bad repair | o/s 3 |  |  | 2023-05-04
96 | Leith Walk Southbound | Capital Cartridges | White lining | Missing?? | o/s 1 |  |  | 2023-05-04
97 | Leith Walk Southbound | N Barton | Obsruction | Signal pole too close | Fault 9 |  |  | 2023-05-04
98 | Leith Walk Southbound | Elm Row | Poor surface | Looks very lumpy | Fault 2 |  |  | 2023-05-04
99 | Newhaven to OT | Melrose Drive - new link to Lindsay Rd | Design? | Why cycling dropped kerb here? | Query design |  |  | 2023-05-04 | 2118
100 | Newhaven to OT | Melrose Drive - new link to Lindsay Rd |  | No foot/cycleway delineation | Query design |  |  | 2023-05-04 | 2118
101 | Newhaven to OT | Melrose Drive | Oustanding | Ped/Cyleway from Asda not started | o/s |  |  | 2023-05-04 | 2122
102 | Newhaven to OT | Melrose Drive | White lining? | No foot/cycleway delineation | Query design |  |  | 2023-05-04 | 2123
103 | Newhaven to OT | Melrose Drive | Outstanding | Ped/Cycleway not finished | o/s |  |  | 2023-05-04 | 2125
104 | Newhaven to OT | Ocean Terminal | Cycle Parking | No permanent cycle parking - just scaffolding | Query design |  |  | 2023-05-04 | 2129
105 | OT to FotW | Ocean Drive | Signalling? | How is traffic managed to avoid conflict with tram at single lane sections? Does it work for cyclists? SEE 107 | Query |  |  | 2023-05-04
106 | Picardy Place | Island | Obstruction | Lamp-post position constricting cycleway/too close to waiting area at crossing to York Place | Query Design |  |  | 2023-07-02 | 2818 | Lamp-post installed in space set aside for cycleway. Contractors have reduced cycleway width to 1.6m and squeezed against lamp-post . Reported to Chris McGarvey.
107 | OT to FotW | Ocean Drive & Constitution St | Signage/ close passing | Cyclists are being close passed and beeped at by drivers (not tram) in the narrow, single lane sections of the route where there is no room to safely overtake. The initial tram route had signs added to warn drivers to give cyclists space as part of the Tram Cycle Safety project - why has this not been done on the tram extension? As this is a new route it would seem appropriate to initially display large signs to warn drivers to stay back. SEE 105 | Fault |  |  | 2023-06-22 |  | Iain Ritson - emails Lack of signage
108 | Picardy Place | Crossing | White lining | When will the white lining for the cycle crossing to Broughton St be completed? The existig lines put cyclists in danger. | Query |  |  | 2023-06-22
109 | Leith Walk Southbound | Dalmeny St | Continuous footway | Near miss reported on Twitter - Driver coming out of Dalmeny Street without stopping. | Query 1 |  |  | 2023-07-19

## Status
Ref | General area | Location | Situation |  | Status | Date updated | Update | Date added | Photo | Comment
4 | Leith Walk | General | Crossing | Do all the junctions with cycle facilities support cyclists U-turns? (Manderston St looks very awkward.) | Query |  |  | 2023-05-04
5 | Leith Walk | General | Resurfacing | Will resurfacing of adjacent streets eg Montgomery and Brunswick be carried out? | Query |  |  | 2023-05-04
70 | Leith Walk | General | Cycleway delineation | Is anything further planned to aid cycleway delineation for partially sighted. Are cyclists still having problems with it? | Query |  |  | 2023-05-04
72 | Leith Walk | General | White lining | When will it all be finished? | Query |  |  | 2023-05-04
10 | Leith Walk | Leith Walk | Pavement Parking | What is proposed to resolve the issues with pavement parking? | Query |  |  | 2023-05-04
11 | Leith Walk | Leith Walk | Driver behaviour | Is there still a problem with illegal manoeuvres eg Left turn into London Road and Strraight across from McDonald Rd into Brunswick? | Query |  |  | 2023-05-04
12 | Leith Walk | Leith Walk | Driver behaviour | What is proposed re Brunswick St? | Query |  |  | 2023-05-04
20 | Leith Walk Northbound | Annandale St | Barriers | Why are the barriers here - no signage. Is it to show that cycleway is closed? | Query |  |  | 2023-05-04
48 | Leith Walk Northbound | Chinese Mkt | Crossing | Cycle stop line and cycle signal - when are cyclists held at ped signalised crossings? Just on pedestrian phase? | Query |  |  | 2023-05-04
7 | Leith Walk Northbound | Elm Row | Under construction | When will Elm Row cycleways be completed? | Query |  |  | 2023-05-04
35 | Leith Walk Northbound | General | General | What will happen re items that TtN are not addressing? | Query |  |  | 2023-05-04
8 | Leith Walk Northbound | Leith Walk | Under construction | When will Leith Walk cycleway be completed and officially OPEN | Query |  |  | 2023-05-04
22 | Leith Walk Northbound | Leith Walk | Other works | Is the the raised white lining from the temporary cycleway going to be removed? | Query |  |  | 2023-05-04
26 | Leith Walk Northbound | Leith Walk | Buffer Zone | What is happening about the buffer zone incursions? | Query |  |  | 2023-05-04
6 | Leith Walk Northbound | London Road | Under construction | When will cycleway from Omni to London Road be completed? | Query |  |  | 2023-05-04
52 | Leith Walk Northbound | Lorne Street | Crossing | Signalised ped crossing but no cycle stop signal. | Query |  |  | 2023-05-04 |  | As cycleway is set back from carriageway - ie "floating" crossing?
105 | OT to FotW | Ocean Drive | Signalling? | How is traffic managed to avoid conflict with tram at single lane sections? Does it work for cyclists? SEE 107 | Query |  |  | 2023-05-04
108 | Picardy Place | Crossing | White lining | When will the white lining for the cycle crossing to Broughton St be completed? The existig lines put cyclists in danger. | Query |  |  | 2023-06-22
25 | Leith Walk Northbound | Leith Walk | Cycleway geometry | Have all the non-conformant tight turns been remedied? | Query (Fault 4) |  |  | 2023-05-04
23 | Leith Walk | Leith Walk | Other works | Are all the broken slabs going to be replaced? | Query (Fault 5) |  |  | 2023-05-04
69 | Leith Walk | General | Poor surface | What sections are being resurfaced and when? | Query / Some Fault 2? |  |  | 2023-05-04
33 | Leith Walk Northbound | Leith Walk | Poor surface | When will all the temporary lampost hole repairs be completed? | Query ? | 2023-06-22 | Completed? | 2023-05-04
13 | Leith Walk Northbound | Leith Walk | Driver behaviour | What is proposed re Driver Behaviour eg re continuous footways; pavement parking; illegal manoeuvres? | Query 1 |  |  | 2023-05-04
109 | Leith Walk Southbound | Dalmeny St | Continuous footway | Near miss reported on Twitter - Driver coming out of Dalmeny Street without stopping. | Query 1 |  |  | 2023-07-19
93 | Leith Walk Southbound | Albert Street | Crossing Design | Crossing from Northbound very tight if doing a U-turn | Query design |  |  | 2023-05-04
82 | Leith Walk Southbound | Lorne Street | Crossing | No cycle stop line or signals - as elsewhere? | Query design |  |  | 2023-05-04 |  | Is this because the cycleway is set back?
89 | Leith Walk Southbound | Pilrig St jn | Cycleway Design | No stop signal for southbound cyclists eg for when pedestrians and cyclists crossing | Query design |  |  | 2023-05-04
102 | Newhaven to OT | Melrose Drive | White lining? | No foot/cycleway delineation | Query design |  |  | 2023-05-04 | 2123
99 | Newhaven to OT | Melrose Drive - new link to Lindsay Rd | Design? | Why cycling dropped kerb here? | Query design |  |  | 2023-05-04 | 2118
100 | Newhaven to OT | Melrose Drive - new link to Lindsay Rd |  | No foot/cycleway delineation | Query design |  |  | 2023-05-04 | 2118
104 | Newhaven to OT | Ocean Terminal | Cycle Parking | No permanent cycle parking - just scaffolding | Query design |  |  | 2023-05-04 | 2129
106 | Picardy Place | Island | Obstruction | Lamp-post position constrciting cycleway/too close to waiting area at crossing to York Place | Query Design |  |  | 2023-07-02 | 2818 | Lamp-post installed in space set aside for cycleway. Contractors have reduced cycleway width to 1.6m and squeezed against lamp-post . Reported to Chris McGarvey.
71 | Leith Walk Southbound | Manderston St | Cycle crossing | Different design from the crossroads junctions. Why no red surfacing? What is the phasing? How do southbound cyclists turn right for a U-turn? | Query? | 2023-06-20 | Cycle signals only seem to change in phase after a tram passes. South ped signal off. | 2023-05-04 | 2064/2065
17 | Leith Walk Northbound | Elm Row | Crossing | No signals for westbound cyclists | ??? |  |  | 2023-05-04
34 | Leith Walk Northbound | Red Cross (McD Rd) | Buffer Zone | Large deviation for tiny inspection cover couldn't it be covered? | Design |  |  | 2023-05-04
53 | Leith Walk Northbound | Springfield St / General | Continuous footway | Cycle symbol on South side should be nearer to jn so that cyclists from Springfield St see that flow is northbound. | Design |  |  | 2023-05-04 |  | Needs applying elsewhere and relates to cyclists' u-turns to reach eastern cycleway
36 | Leith Walk Northbound | The Walnut | Cycleway geometry | Cycleway changes direction twice in short space - combine into single direction change | Design |  |  | 2023-05-04
74 | Leith Walk Southbound | Salvation Army | Cycleway geometry | 2-stage deviation should be combined | Design |  |  | 2023-05-04
64 | Leith Walk Northbound | Foot of the Walk | Crossing | Unfinished. Some cycle signals covered up or turned off but pushbutton illuminated. | Design? |  |  | 2023-05-04 | 2054/ 2055
9 | Leith Walk Northbound | London Road | ASL | ASL needed Northbound from Picardy Place. Ideally to link with on-road cycleway. Also to accommodate right-turning on-road cyclists? Include cycle early release. | Design |  |  | 2023-05-04
3 | Leith Walk Northbound | Picardy Place/ Antigua Street | Add facility | Cycleway along North side from Toucan to Gayfield Square. | Design |  |  | 2023-05-04 |  | Awaiting survey to determine whether there is space
2 | Leith Walk Northbound | York Place | Crossing | Toucan from North cycleway completed. Cross via island: 1. Crossing is staggered with little room in the middle (on the platform) and lots of poles in the way, making it virtually unrideable. 2. Crossing lights are live to the main island but crossing goes nowhere except tramstop island and assume trams aren't stopping yet? 2. Crossing needs to be adapted to support northbound cyclists joining the carriageway. | Design | 2023-06-22 | Crossing completed except for Northbound cycle signals. Design for cycle route to Gayfield awaited. (see 3) | 2023-05-04 | 1991 1992 1993
107 | OT to FotW | Ocean Drive & Constitution St | Signage/ close passing | Cyclists are being close passed and beeped at by drivers (not tram) in the narrow, single lane sections of the route where there is no room to safely overtake. The initial tram route had signs added to warn drivers to give cyclists space as part of the Tram Cycle Safety project - why has this not been done on the tram extension? As this is a new route it would seem appropriate to initially display large signs to warn drivers to stay back. SEE 105 | Fault |  |  | 2023-06-22 |  | Iain Ritson - emails Lack of signage
49 | Leith Walk Northbound | Chinese Mkt | Poor surface | Puddles before and after | Fault 2 |  |  | 2023-05-04
15 | Leith Walk Northbound | Gayfield Square | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
56 | Leith Walk Northbound | Leith Depot | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
30 | Leith Walk Northbound | McD Rd library | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
59 | Leith Walk Northbound | Mother Superior | Poor surface | Large puddle | Fault 2 |  |  | 2023-05-04 | 2045
63 | Leith Walk Northbound | No 34 | Poor surface | Large puddle in cycleway followed by general puddling | Fault 2 |  |  | 2023-05-04 | 2052/ 2053
61 | Leith Walk Northbound | No 62 | Other works | Large puddle on footway | Fault 2 |  |  | 2023-05-04 | 2048
47 | Leith Walk Northbound | Pilrig area? | Poor surface | Puddles | Fault 2 |  |  | 2023-05-04
44 | Leith Walk Northbound | Pilrig St jn | Poor surface | Puddle on south side | Fault 2 |  |  | 2023-05-04
38 | Leith Walk Northbound | Places Gym | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
55 | Leith Walk Northbound | Steads Place | Poor surface | Lots of puddles to north | Fault 2 |  |  | 2023-05-04
76 | Leith Walk Southbound | Allander House | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
80 | Leith Walk Southbound | Casino Gaming | Poor surface | Puddles | Fault 2 |  |  | 2023-05-04
98 | Leith Walk Southbound | Elm Row | Poor surface | Looks very lumpy | Fault 2 |  |  | 2023-05-04
75 | Leith Walk Southbound | 129 | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
78 | Leith Walk Southbound | ex Tram Offices | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
87 | Leith Walk Southbound | Home essentials | Poor surface | Puddles | Fault 2 |  |  | 2023-05-04
68 | Leith Walk Southbound | Papa John's | Poor surface | Puddles | Fault 2 |  |  | 2023-05-04 | 2061
90 | Leith Walk Southbound | Pilrig St jn | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
73 | Leith Walk Southbound | Tip Top Tresses | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
81 | Leith Walk Southbound | William Hill | Poor surface | Puddling | Fault 2 |  |  | 2023-05-04
45 | Leith Walk Northbound | Pilrig St jn | Signals | Call signal refers to pedestrians and unclear what crossing it's for | Fault 3 |  |  | 2023-05-04 |  | Also at Annandale
18 | Leith Walk Northbound | Annandale St | Crossing | Cyclist call button says "pedestrians" and "signal opposite". Isn't obviously for cycle crossing as in line w ped xing of Annandale. | Fault 3+ |  |  | 2023-05-04
24 | Leith Walk Northbound | 5th Season Vintage | Cycleway geometry | Very tight turn in cycleway | Fault 4 |  |  | 2023-05-04
57 | Leith Walk Northbound | Leith Depot/ General | Cycleway geometry | Turn too tight | Fault 4 |  |  | 2023-05-04 | 2043
85 | Leith Walk Southbound | Jameson Place | Cycleway geometry | Sharp turn | Fault 4 |  |  | 2023-05-04
27 | Leith Walk Northbound | Emma Hall | Other works | Broken slab | Fault 5 |  |  | 2023-05-04
41 | Leith Walk Northbound | Sainsbury | Other works | Broken slab | Fault 5 |  |  | 2023-05-04
54 | Leith Walk Northbound | Steads Place | Other works | Damaged slabs | Fault 5 |  |  | 2023-05-04
43 | Leith Walk Northbound | Scotmid | Poor surface | Cracked edging | Fault 6 |  |  | 2023-05-04
29 | Leith Walk Northbound | Tribe Yoga area | Poor surface | Cycleway edge breaking up. (General problem?) | Fault 6 |  |  | 2023-05-04
32 | Leith Walk Northbound | McD Rd library | Surface | Wrong surface finish | Fault 7 |  |  | 2023-05-04
66 | Leith Walk Southbound | Foot of the Walk | Surface | some sections with white chippings - eg at Argonaut Books | Fault 7 |  |  | 2023-05-04 | 2058
58 | Leith Walk Northbound | Leith Depot/ General | Obstruction | Tram warning signpole too close to cycleway | Fault 9 |  |  | 2023-05-04 | 2044
39 | Leith Walk Northbound | Sainsbury | Obstruction | Sign-pole too close to cycleway at informal crossing | Fault 9 |  |  | 2023-05-04
86 | Leith Walk Southbound | Jameson Place | Obstruction | Pole in cycleway | Fault 9 |  |  | 2023-05-04 | 2082
83 | Leith Walk Southbound | Lorne Street | Obstruction | Bin a bit close to cycleway | Fault 9 |  |  | 2023-05-04
97 | Leith Walk Southbound | N Barton | Obsruction | Signal pole too close | Fault 9 |  |  | 2023-05-04
62 | Leith Walk Northbound | Casselbank | Obstruction? | Pole quite close to cycleway (over 500mm though) | Fault 9? |  |  | 2023-05-04 | 2050/ 2051
77 | Leith Walk Southbound | ex Tram Offices | Other works | Crossing needs to be done | o/s |  |  | 2023-05-04
101 | Newhaven to OT | Melrose Drive | Oustanding | Ped/Cyleway from Asda not started | o/s |  |  | 2023-05-04 | 2122
103 | Newhaven to OT | Melrose Drive | Outstanding | Ped/Cycleway not finished | o/s |  |  | 2023-05-04 | 2125
19 | Leith Walk Northbound | Annandale St | White lining | White lining on North side oustanding | o/s 1 |  |  | 2023-05-04
50 | Leith Walk Northbound | Balfour St jn | White lining | oustanding | o/s 1 |  |  | 2023-05-04
28 | Leith Walk Northbound | Emma Hall | White lining | Oustanding | o/s 1 |  |  | 2023-05-04
16 | Leith Walk Northbound | Gayfield Square | White lining | Oustanding at bus stop | o/s 1 |  |  | 2023-05-04
96 | Leith Walk Southbound | Capital Cartridges | White lining | Missing?? | o/s 1 |  |  | 2023-05-04
84 | Leith Walk Southbound | Jameson Place | White lining | Ramp without arrows | o/s 1 |  |  | 2023-05-04
79 | Leith Walk Southbound | Smiths Place | White lining | No arrows on ramp | o/s 1 |  |  | 2023-05-04
37 | Leith Walk Northbound | Engine Yard | Poor surface | Repair needed but not marked | o/s 3 |  |  | 2023-05-04
14 | Leith Walk Northbound | Gayfield Square | Collapsed manhole | Temporary cover in place - needs fixing. | o/s 3 |  |  | 2023-05-04
42 | Leith Walk Northbound | No 372 | Poor surface | Repair needed - marked | o/s 3 |  |  | 2023-05-04
46 | Leith Walk Northbound | Pilrig St jn | Poor surface | North side - collapsed manhole | o/s 3 |  |  | 2023-05-04
40 | Leith Walk Northbound | Sainsbury | Poor surface | Large manhole cover missing | o/s 3 |  |  | 2023-05-04
92 | Leith Walk Southbound | A-os Barbers | Poor surface | Bad repair - ex lampost? | o/s 3 |  |  | 2023-05-04
95 | Leith Walk Southbound | Gateway Apartments | Poor surface | Bad repair | o/s 3 |  |  | 2023-05-04
94 | Leith Walk Southbound | Green Leith | Poor surface | Bad repair - ex lampost? | o/s 3 |  |  | 2023-05-04
88 | Leith Walk Southbound | Iona Street | Poor surface | Bad repair | o/s 3 |  |  | 2023-05-04
67 | Leith Walk Southbound | TSB | Poor surface | Poor repair | o/s 3 |  | Maybe complete if was from lamp post removal | 2023-05-04 | 2060
91 | Leith Walk Southbound |  | Poor surface | Bad repair - ex lampost? | o/s 3 |  |  | 2023-05-04
51 | Leith Walk Northbound | Rome Barber | White lining | Cycle logo needs redone | o/s 4 |  |  | 2023-05-04
60 | Leith Walk Northbound | Mother Superior | Crossing | No cycle stop line or signals | o/s 4? |  |  | 2023-05-04 | 2045
65 | Leith Walk Southbound | Foot of the Walk | Cycleway geometry | Very narrow lane on SE corner | o/s? |  |  | 2023-05-04 | 2056/ 2057 | Spokes told that this would be fixed?
21 | Leith Walk Northbound | Annandale St | Surface | Access slip to cycleway from Annandale appears unfinished and no red chips. | Closed | 2023-06-22 | Completed | 2023-05-04
1 | Leith Walk Northbound | York Place | Junction | Jn now fully open and CCWEL cycleway re-opened. | Closed |  |  | 2023-05-04 | 1990
31 | Leith Walk Northbound | McD Rd library | Poor surface | Badly repaired. Former lampost position? | Closed ? | 2023-06-22 | Completed ? | 2023-05-04